TEAM (Company) :

1-MalakHendawy

2-Logain Mohamed

3-Karim Wael

4-Ali Mohamed

Escalation levels : CO-Head (Youssef abdelaal) ,Head(Malak Elghamrawy)

TEAM(Brand) :

1-Natalie Tarek

2-Jana Walid

3-Seif Allah Yehia

Escalation levels : CO-Head (Pola Raouf ) ,Head(Malak Elghamrawy)

Tasks are the same for both teams :

Goal confirm with 2 companies and One Brand

- Each member of the team must bring 5 companies/brands with their contact information so we can reach out to them.

- Then, try to confirm at least one company to make sure they are able to come and that the process can start (pre-confirmation).

- After that, we will filter and choose from the collected companies through a discussion with the team and the co-heads to identify the most valuable and impactful option.

- Once the company is selected, we will decide on the deals we want to make with them as a team.(+++mention to them what is our and heir benefit)

- Prepare a list of the deals you chose before sending anything.

- All emails and messages must be formal.

- Then I (Malak) will send you the pricing, and you will forward it to the companies and proceed with confirmation.

- As the head, I will handle getting approval from the university PR, the dean, and any required authorities.

1. Research & Selection – Deadline: 25 Nov
Each member chooses one company/brand and submits:

- Name

- Why they chose it

- Contact info

- Exact person to contact

2. First Contact – Deadline: 26 Nov
Each member contacts their target through email, LinkedIn, or phone.
Goal: get a response and open communication.

3. Pre-Confirmation – 27–28 Nov (Sololy)
If the company/brand replies positively, the member asks ONLY:

- Can you come between 1–10 Dec?

- What activation do you prefer?

- What kind of presence do you want?
Members must NOT negotiate money or details.
The moment a reply comes, they inform you + co-heads.

4. Team Negotiation (keda el mfrod maana 4 lw company w 3 lw brand ashan kol wahed hyconfirm maa whda w n5tar 2 aw 1 mn el 4 ) 
If the company/brand is available:

- Co-heads + Head PR approve the direction.

- Then the entire team joins the negotiation call/meeting.
Only the Head PR handles final numbers and pricing.

5. Final Confirmation – 29–30 Nov
After negotiation:

- Head PR sends the formal confirmation

- Company/brand gives final approval
PR confirms date, payment, or paperwork.

PR DEADLINES (Companies & Brands)
Goal: 2 companies + 1 brand confirmed

25 Nov – Research
Each member submits:

- 1 chosen target + full contact info

- 5 extra companies/brands with contact info

26 Nov – First Contact
Each member contacts their chosen target and gets a response.

27–28 Nov – Pre-Confirmation
If they reply:

- Ask availability (1–10 Dec)

- Ask activation type

- No negotiation

- Report immediately to co-head + Head PR

29–30 Nov – Final Steps

- Team + co-head + Head PR choose final options

- Head PR handles negotiation + pricing

- Head PR sends final confirmation

- Papers submitted to university

Solo Tasks (Each Member)

- 25 Nov: Submit 1 chosen target + 5 extra options with contacts.

- 26 Nov: Contact your chosen target and get a reply.

- 27–28 Nov: If they reply, ask availability + activation (no negotiation) and report immediately.

Group Tasks

- 29–30 Nov: Team + co-head + Head PR choose final options, join negotiation call.

- Head PR confirms pricing and handles university paperwork.